{"text_format":"3","workbook":"xls","n_sheets":4,"sheets":["表","接口文档","其他附属信息","危化版业务信息"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"表","index":0,"n_rows":45,"n_cols":14,"rows_kept":45,"merged":[[0,0,0,13],[1,0,1,2],[1,7,1,13],[2,2,2,3],[3,0,5,0],[3,1,5,1],[3,2,4,2],[3,3,3,4],[4,3,4,4],[5,3,5,4],[6,0,44,0],[6,1,44,1],[6,2,9,2],[6,3,6,4],[6,9,44,9],[6,10,44,10],[6,11,44,11],[6,13,44,13],[7,3,7,4],[8,3,8,4],[9,3,9,4],[10,2,25,2],[10,3,15,3],[16,3,19,3],[20,3,21,3],[22,3,25,3],[26,2,26,4],[27,2,38,2],[27,3,31,3],[32,3,38,3],[39,2,39,4],[40,2,40,4],[41,2,43,2],[41,3,41,4],[42,3,42,4],[43,3,43,4],[44,2,44,4]],"flags":["formulas_cached_only"]}
["危化企业信息信息报送平台目计划和实施进度表"]
["项目名称：危化企业信息信息报送平台"]
["阶段","工作任务","任务分解",null,null,"工作量（人/天）（开发）","工作量（人/天）（测试）","责任人","协助人员","计划完成时间","实际完成时间","当前状态","当前进度情况","备注\n（延期原因请在这里说明）"]
[1,"运维","内蒙古园区作业票业务更新","1、包头特殊作业对应区域手动维护，需要等待企业反馈，然后手动推送",null,1,2,"刘俊","王轩","—","—",null,null,"统计出所有的作业票数据后，交给对应企业维护信息"]
[{"$nulls":3},"2、包头园区-隐患补充，补充后手动推送",null,1]
[null,null,"河北省危化平台","3、专项检查手动推送",null,1]
[3,"推送平台","1、企业账号及信息维护","1、基础信息维护",null,3,"—","刘俊","赵梦、鲁红霞","—","—",null,null,"对外对接功能"]
[{"$nulls":3},"2、企业管理",null,3,null,"刘俊"]
[{"$nulls":3},"3、日志查询功能",null,2,null,"刘俊"]
[{"$nulls":3},"4、错误数据查询及查看",null,2,null,"刘俊"]
[null,null,"2、上报接口开发","1、新功能开发（省平台）","1、上报三同时数据",1,null,"刘俊","赵梦、鲁红霞"]
[{"$nulls":4},"2、装置开停车和大检修管理信息",1,null,"刘俊"]
[{"$nulls":4},"3、特殊作业安全管控",1,null,"刘俊"]
[{"$nulls":4},"4、人员定位数据",1,null,"刘俊"]
[{"$nulls":4},"5、雷电预警",1,null,"刘俊"]
[{"$nulls":4},"6、基础代码开发",5,null,"刘俊"]
[{"$nulls":3},"2、新功能开发（园区）","1、东圣园区-双控",5,null,"刘俊"]
[{"$nulls":4},"2、东圣园区-人员信息",5,null,"刘俊"]
[{"$nulls":4},"3、东圣园区-特证",5,null,"刘俊"]
[{"$nulls":4},"4、东圣园区-人员定位",5,null,"刘俊"]
[{"$nulls":3},"3、功能迁移（省平台）","1、危化版-双控",5,null,"刘俊"]
[{"$nulls":4},"2、危化版-专项",5,null,"刘俊"]
[{"$nulls":3},"4、功能迁移（园区）","1、东江-双控",5,null,"刘俊"]
[{"$nulls":4},"2、东江-人员定位",5,null,"刘俊"]
[{"$nulls":4},"3、土右-双控",5,null,"刘俊"]
[{"$nulls":4},"4、土右-特殊作业",5,null,"刘俊"]
[null,null,"3、接口文档整理",{"$nulls":4},"刘俊"]
[null,null,"4、数据接受接口开发","1、省平台接口","1、双控",2,null,"刘俊"]
[{"$nulls":4},"2、特殊作业",2,null,"刘俊"]
[{"$nulls":4},"3、人员定位",2,null,"刘俊"]
[{"$nulls":4},"4、专项检查",2,null,"刘俊"]
[{"$nulls":4},"5、接口规范文档编写",2,null,"刘俊"]
[{"$nulls":3},"2、园区","1、东江-双控",2,null,"刘俊"]
[{"$nulls":4},"2、包头-双控",2,null,"刘俊"]
[{"$nulls":4},"3、包头-特殊作业",2,null,"刘俊"]
[{"$nulls":4},"4、石家庄-双控",2,null,"刘俊","赵梦、鲁红霞"]
[{"$nulls":4},"4、石家庄-人员定位",2,null,"刘俊"]
[{"$nulls":4},"4、石家庄-特殊作业",2,null,"刘俊"]
[{"$nulls":4},"5、接口规范文档编写",2,null,"刘俊"]
[null,null,"5、接口加密",null,null,2,null,"刘俊"]
[null,null,"6、对应企业获取接口文档页面（类似课件商城）",{"$nulls":4},"刘俊","—"]
[null,null,"7、千万级数据数据库设计","1、数据库存储方案",{"$nulls":3},"刘俊","房家凯"]
[{"$nulls":3},"2、数据库设计",{"$nulls":3},"刘俊","房家凯"]
[{"$nulls":3},"3、数据库数据备份方案",{"$nulls":3},"刘俊","房家凯"]
[null,null,"8、白名单系统功能设计",{"$nulls":4},"刘俊","房家凯"]

{"sheet":"接口文档","index":1,"n_rows":2,"n_cols":3,"rows_kept":2,"flags":["formulas_cached_only"]}
[]
[null,1,"实际工作时间"]

{"sheet":"其他附属信息","index":2,"n_rows":8,"n_cols":5,"rows_kept":8,"flags":["formulas_cached_only"]}
[{"$nulls":4},"备注"]
[null,1,"时序数据库","https://www.tigerdata.com/developers","时序数据库官网"]
[null,2,"危化版定时任务","https://www.xuxueli.com/","XXL定时任务官网"]
[null,3,"危化版定时任务git","http://47.92.113.182:3000/integrated_whb/integrated_whb_scheduled.git","危化版定时任务git"]
[null,4,"危化版定时任务管理页面","http://39.100.115.58:28080/xxl-job-admin/jobinfo?jobGroup=1","账号admin 密码O@CiVIB?FOP+7TsDj "]
[null,5,"危化版定时任务管理页面（测试环境）","http://192.168.20.230:28080/xxl-job-admin/jobgroup","230的xljob密码是 admin admin"]
[null,6,"危化版正式环境配置","jdbc:mysql://47.92.102.56:33068/integrated_whb?serverTimezone=UTC&useSSL=false&useUnicode=true&characterEncoding=utf-8","root/Admin@@admin88888"]
[null,7,"唐山园区上报数据可视化系统","http://47.92.102.56:8080/#/hidden_danger_government/ledger/view?HIDDEN_ID=3d01d65e09704a5fa6df8ad5db7631c7&LIST_TYPE=1","13293211008/ Djhg@Pwd123"]

{"sheet":"危化版业务信息","index":3,"n_rows":3,"n_cols":4,"rows_kept":3,"flags":["formulas_cached_only"]}
[]
[null,1,"包头园区对接企业","包头市寰达新能源有限责任公司（150280136）-这四家只推八项作业\n包头市新兴盛能源有限责任公司（150210116）-这四家只推八项作业\n包头市创美新能源有限责任公司-这四家只推八项作业\n包头市路通高科新材料有限责任公司-这四家只推八项作业\n内蒙古中皓精细化工有限公司-只推双控"]
[null,2,"内蒙古省平台对接","内蒙古盈通能源有限"]